## Gantt Progress Tracker
STI SYNC — SYSTEM DEVELOPMENT GANTT CHART & DUAL-TIMELINE TRACKER
Dual-Timeline Comparison: Expected Projections (Purple) vs. Actual Implementation & Accomplishment Progress (Green/Yellow/Red)
TIMELINE LEGEND: | 🟣 Expected Projection | 🟢 Complete (Actual) | 🟡 Incomplete (Actual) | 🔴 Not Started (Actual)
Module / Category | Sub-Component & Feature | Key Functions & CRUD Details | Timeline Status | FEBRUARY 2026 |  |  |  | MARCH 2026 |  |  |  | APRIL 2026 |  |  |  | MAY 2026 |  |  |  | JUNE 2026 |  |  |  | JULY 2026 |  |  |  | AUGUST 2026 |  |  |  | SEPTEMBER 2026 |  |  |  | OCTOBER 2026 |  |  |  | NOVEMBER 2026
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
0. PROJECT MANAGEMENT, REQUIREMENTS & DOCUMENTATION (FEBRUARY – MAY 2026)
Requirements Gathering | SAO Staff & Student Officers Needs Analysis | Interview SAO advisers, campus officers, and students to define system scope & workflows (Feb 2026 – Apr 2026) | 🟣 Projected Plan | bar: FEBRUARY 2026 W1 to MARCH 2026 W4
🟢 Complete (Actual) | bar: FEBRUARY 2026 W3 to APRIL 2026 W1
Requirements Gathering | Institutional Workflow & Compliance Specs | Gather event approval workflows, liquidation policies, gate security rules & fine penalty guidelines (Mar 2026 – May 2026) | 🟣 Projected Plan
🟢 Complete (Actual)
Planning & Architecture | System Architecture & Tech Stack Planning | Define database schema (Firestore & Drift SQLite), state management, API routes & tech stack architecture (Mar 2026 – Apr 2026) | 🟣 Projected Plan | bar: MARCH 2026 W1 to APRIL 2026 W2
🟢 Complete (Actual) | bar: MARCH 2026 W2 to APRIL 2026 W3
Planning & Architecture | UI/UX Wireframing & Design System | Design UI/UX mockups, glassmorphic themes, responsive layouts for Web App & Flutter Mobile App (Apr 2026 – May 2026) | 🟣 Projected Plan
🟢 Complete (Actual)
Project Documentation | Technical Specs & Developer Documentation | Document system API endpoints, database schemas, deployment setup, and security protocols (Feb 2026 – Nov 2026) | 🟣 Projected Plan
🟡 Incomplete (Actual)
Project Documentation | User Manuals & Administrative Guides | Create step-by-step user guide manuals for SAO Admin, Club Officers, and Gatekeeper Scanners (Apr 2026 – May 2026) | 🟣 Projected Plan
🟡 Incomplete (Actual)
1. SAO ADMIN WEB DASHBOARD & MODULES
Authentication & Gate | SAS Admin Login Screen & Gateway | Role verification, SAS admin credentials auth (SASAdminLogin.tsx) | 🟣 Projected Plan | bar: JUNE 2026 W1 to JUNE 2026 W2
🟢 Complete (Actual) | bar: JUNE 2026 W2 to JUNE 2026 W3
Authentication & Gate | Route Guard & Session Auth Context | Admin layout shell protection, route guard, active adviser profile hook | 🟣 Projected Plan
🟢 Complete (Actual)
Admin Dashboard | Overview Stat Metric Cards | Static UI cards (5 approvals, 3 liquidations, 24 active orgs, 42 events) — pending live stream link | 🟣 Projected Plan | bar: JUNE 2026 W2 to JUNE 2026 W4
🟡 Incomplete (Actual) | bar: JUNE 2026 W3 to JULY 2026 W1
Admin Dashboard | Live System Activity Feed & Approvals Queue | Mock pending approvals queue & mock organization activity list (Dashboard.tsx) | 🟣 Projected Plan
🟡 Incomplete (Actual)
Admin Dashboard | Campus Activity Chart | Recharts bar chart displaying weekly events held & scan volume (Mock Data) | 🟣 Projected Plan | bar: JUNE 2026 W3 to JUNE 2026 W4
🟡 Incomplete (Actual) | bar: JUNE 2026 W4 to JULY 2026 W1
Admin Dashboard | Quick Action Navigation Grid | UI shortcut buttons to generate report, manage orgs, review liquidations | 🟣 Projected Plan
🟡 Incomplete (Actual)
Student Registry | Registry Dashboard & Category Summary | Registry summary cards, status counts (Pending, Active, Re-enrollment, Inactive, Archived) | 🟣 Projected Plan | bar: JUNE 2026 W3 to JULY 2026 W1
🟢 Complete (Actual) | bar: JUNE 2026 W4 to JULY 2026 W2
Student Registry | Pending Verification & AI OCR Inspection | Side-by-side selfie vs school ID inspection, OCR score check, approval/rejection modal | 🟣 Projected Plan
🟢 Complete (Actual)
Student Registry | Account Approval / Rejection (CRUD Update) | Update student status to ACTIVE or return registration with revision notes (student.service.ts) | 🟣 Projected Plan | bar: JUNE 2026 W4 to JULY 2026 W2
🟢 Complete (Actual) | bar: JULY 2026 W1 to JULY 2026 W3
Student Registry | Active Students Masterlist & Search | Live Firestore student table, course & section filters, student detail modal (ActiveStudents.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Student Registry | Manual Student Registration Modal | Add student manually with ID number, course, section, year level input (AddStudentManuallyModal.tsx) | 🟣 Projected Plan | bar: JULY 2026 W1 to JULY 2026 W3
🟢 Complete (Actual) | bar: JULY 2026 W2 to JULY 2026 W4
Student Registry | Re-Enrollment & Term Promotion Engine | Semester re-enrollment tracking, promote student year levels per academic year (ReEnrollmentManagement.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Student Registry | Inactive & Suspended Students Management | Roster of inactive & suspended students, suspend modal with penalty reason, reactivate student | 🟣 Projected Plan | bar: JULY 2026 W2 to JULY 2026 W4
🟢 Complete (Actual) | bar: JULY 2026 W3 to AUGUST 2026 W1
Student Registry | Archived & Graduated Student Records | Historical list of archived & graduated students, unarchive action (ArchivedGraduates.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Student Registry | CSV Bulk Student Import / Export | Batch parse student records from CSV, export student masterlist (UI placeholder) | 🟣 Projected Plan | bar: JULY 2026 W1 to JULY 2026 W3
🟡 Incomplete (Actual) | bar: JULY 2026 W3 to AUGUST 2026 W1
Organizations | Organization Cards Grid & Status Filter | Live org stream (useOrganizationStream) with member counts, org type badges, acronym logos | 🟣 Projected Plan
🟢 Complete (Actual)
Organizations | Create Organization Modal (CRUD Create) | Create new org document in Firestore with logo upload & adviser assignment (CreateClubModal.tsx) | 🟣 Projected Plan | bar: JULY 2026 W2 to JULY 2026 W4
🟢 Complete (Actual) | bar: JULY 2026 W3 to AUGUST 2026 W1
Organizations | Edit Organization Modal (CRUD Update) | Update existing org details, acronym, type, logo URL (EditOrganizationModal.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Organizations | Org Status Modal (Suspend / Archive / Reactivate) | Change org operational status (Active, Suspended, Archived) in Firestore (OrganizationStatusModal.tsx) | 🟣 Projected Plan | bar: JULY 2026 W3 to AUGUST 2026 W1
🟢 Complete (Actual) | bar: JULY 2026 W4 to AUGUST 2026 W2
Organizations | Organization Profile Detail View Modal | Modal showing org profile details, mission/vision, adviser info & member list | 🟣 Projected Plan
🟡 Incomplete (Actual)
Event Approvals & SAO Wizard | Proposal Review & Approval Workflow | List pending proposals with tab filters, quick approve/reject, rejection reason (EventApprovals.tsx) | 🟣 Projected Plan | bar: JULY 2026 W2 to AUGUST 2026 W1
🟢 Complete (Actual) | bar: JULY 2026 W3 to AUGUST 2026 W2
Event Approvals & SAO Wizard | Full Event Proposal Review Workspace | Comprehensive proposal inspector modal with budget breakdown & attached compliance docs (EventProposalReview.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Event Approvals & SAO Wizard | 7-Step SAO Event Creation Wizard (Steps 1 to 7) | Details, Schedule, Participants, Staff, Budget, Docs, Publish wizard modal (SaoEventCreationModal.tsx) | 🟣 Projected Plan | bar: JULY 2026 W3 to AUGUST 2026 W3
🟢 Complete (Actual) | bar: JULY 2026 W4 to AUGUST 2026 W4
Event Approvals & SAO Wizard | Draft Resumption & Wizard State Sync | Save SAO event draft, calculate draft progress step, resume draft in wizard (useDraftEvents) | 🟣 Projected Plan
🟢 Complete (Actual)
Event Approvals & SAO Wizard | Detailed Event View & Collection Progress | Overview grid, collection progress bar (collected vs expected total), paid/unpaid counter (EventDetailView.tsx) | 🟣 Projected Plan | bar: AUGUST 2026 W1 to AUGUST 2026 W3
🟢 Complete (Actual) | bar: AUGUST 2026 W2 to AUGUST 2026 W4
Event Approvals & SAO Wizard | Student Payables & QR Unlock Manager | Search student payables, Mark Paid / Unpaid, automatically unlock/lock student QR ticket | 🟣 Projected Plan
🟢 Complete (Actual)
Attendance Monitoring | Real-time Gate Scan Feed & Logs Stream | Live attendance stream (useAttendanceStream) showing check-in/check-out timestamps & gatekeeper info | 🟣 Projected Plan | bar: AUGUST 2026 W1 to SEPTEMBER 2026 W1
🟢 Complete (Actual) | bar: AUGUST 2026 W2 to SEPTEMBER 2026 W2
Attendance Monitoring | Multi-Criteria Filter Toolbar | Filter toolbar by department, course, section, year level, session window, status (AttendanceFilterToolbar.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Attendance Monitoring | Campus Attendance Overview Chart | Recharts bar chart comparing registered vs. attended vs. absent students across active events | 🟣 Projected Plan | bar: AUGUST 2026 W2 to AUGUST 2026 W4
🟢 Complete (Actual) | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W1
Attendance Monitoring | Institutional Event Fine Control Engine | One-click trigger (recordEventFinePayables) to generate absence/late fine payables in DB | 🟣 Projected Plan
🟢 Complete (Actual)
Attendance Monitoring | Attendance Log Excel Export Preview Modal | Export Preview Modal showing tabular export data (AttendanceExportPreviewModal.tsx: direct file save pending) | 🟣 Projected Plan | bar: AUGUST 2026 W4 to SEPTEMBER 2026 W2
🟡 Incomplete (Actual) | bar: SEPTEMBER 2026 W2 to SEPTEMBER 2026 W4
Financial Liquidations | Submitted Liquidations List & Status Tabs | Live liquidations stream (useAllLiquidations), status tabs (Pending, Approved, Returned, All) | 🟣 Projected Plan
🟢 Complete (Actual)
Financial Liquidations | Budget vs Actual Variance Calculator | Itemized line items table, allocated vs actual cost comparison, surplus/deficit calculation | 🟣 Projected Plan | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W2
🟢 Complete (Actual) | bar: AUGUST 2026 W4 to SEPTEMBER 2026 W3
Financial Liquidations | Expense Receipt Lightbox Inspector | Full-screen receipt image lightbox modal with vendor & total cost metadata (ReceiptLightboxModal.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Financial Liquidations | Liquidation Approval & Return Workflow | Approve report or return with revision notes to officer (approveLiquidationReport, returnLiquidationReport) | 🟣 Projected Plan | bar: AUGUST 2026 W4 to SEPTEMBER 2026 W4
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W1 to OCTOBER 2026 W1
Financial Liquidations | Admin Liquidation Creation Modal | Create SAO office direct liquidations (OfficerLiquidationModal.tsx with admin context) | 🟣 Projected Plan
🟢 Complete (Actual)
Financial Liquidations | Liquidation Export Preview Modal | Excel export preview modal displaying report summary (LiquidationExportPreviewModal.tsx) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W2 to SEPTEMBER 2026 W4
🟡 Incomplete (Actual) | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W2
Financial Liquidations | Disbursement & Fund Release Audit Trail | Disbursement logs & fund release ledger postings | 🟣 Projected Plan
🟡 Incomplete (Actual)
Certificates Module | Certificate Dashboard & Event Queue | Overview metrics, ready-to-generate completed event queue (CertificateDashboard.tsx) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W1 to SEPTEMBER 2026 W2
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W2 to SEPTEMBER 2026 W3
Certificates Module | Template Library Grid & Upload Options | Card grid of saved cert templates, category filter, template creation trigger (TemplateLibrary.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Certificates Module | Visual Drag-and-Drop Canvas Editor | Interactive canvas editor, place dynamic student name placeholder, font styling, signatures (TemplateEditor.tsx) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W2 to SEPTEMBER 2026 W4
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W1
Certificates Module | Batch Certificate Generator Engine | Generate certs for attended student list, individual preview navigation (GenerateCertificates.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Certificates Module | Full-Screen Certificate Preview Modal | Full-screen high-fidelity cert preview with recipient navigation (PreviewModal.tsx) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W1
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W2
Certificates Module | Multi-Format Export Engine (PNG/PDF) | Resolution picker, format options (PNG/PDF), batch ZIP output progress (ExportModal.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Document Management | Incoming Officers Submissions Queue | Live incoming document stream (useIncomingDocuments), status tabs, reference search (AdminDocuments.tsx) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W2 to OCTOBER 2026 W1
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W2
Document Management | Quick Approve & Quick Reject Popovers | Inline quick action popovers to approve or reject submissions with remarks | 🟣 Projected Plan
🟢 Complete (Actual)
Document Management | Full Document Review Workspace | Dedicated review workspace for proposal compliance inspection (AdminDocumentReview.tsx) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W2
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W3
Document Management | Full-Screen Document Preview Modal | PDF/image document viewer modal (DocumentPreviewModal.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Document Management | Broadcast Document to Clubs Modal | Broadcast SAO memo/template to all or specific orgs, Cloudinary upload (BroadcastModal.tsx) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W2
🟢 Complete (Actual) | bar: OCTOBER 2026 W1 to OCTOBER 2026 W3
Document Management | Sent Broadcast History & Read Tracking | Live stream of sent broadcasts (useSentDocuments), read tracking count per org (SentTab) | 🟣 Projected Plan
🟢 Complete (Actual)
Reports & Analytics | Report Type Selector Cards | Cards selector for Event, Financial, Attendance, and Organization reports (ReportsAnalytics.tsx) | 🟣 Projected Plan | bar: OCTOBER 2026 W1 to OCTOBER 2026 W3
🟡 Incomplete (Actual) | bar: OCTOBER 2026 W3 to NOVEMBER 2026 W1
Reports & Analytics | Event & Attendance Trends Line Chart | Recharts line chart displaying monthly events & attendance trends (Mock Data) | 🟣 Projected Plan
🟡 Incomplete (Actual)
Reports & Analytics | Budget vs Spending & Org Distribution Charts | Bar chart for org budget vs spending and pie chart for org category distribution (Mock Data) | 🟣 Projected Plan | bar: OCTOBER 2026 W2 to NOVEMBER 2026 W1
🟡 Incomplete (Actual) | bar: OCTOBER 2026 W4 to NOVEMBER 2026 W3
Reports & Analytics | Automated PDF Audit Report Generator | One-click export of SAO term activity & audit compliance PDF | 🟣 Projected Plan
🔴 Not Started (Actual)
System & Academic Settings | Academic Semester & Terms Configurator (CRUD) | Live academic stream (useSemesters), configure active school year, semester dates & term toggle (AcademicSemesterSettings.tsx) | 🟣 Projected Plan | bar: OCTOBER 2026 W1 to OCTOBER 2026 W3
🟢 Complete (Actual) | bar: OCTOBER 2026 W2 to OCTOBER 2026 W4
System & Academic Settings | Academic Calendar Events & Holidays | Academic calendar events list & holiday date configurator (AcademicCalendar.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
System & Academic Settings | Budget & Fund Sources Configurator (CRUD) | Live budget stream (useBudgetFunds), allocate fund sources, set org budget caps (BudgetFundSettings.tsx) | 🟣 Projected Plan | bar: OCTOBER 2026 W2 to OCTOBER 2026 W4
🟢 Complete (Actual) | bar: OCTOBER 2026 W3 to NOVEMBER 2026 W1
System & Academic Settings | Departments, Courses & Sections Management (CRUD) | Full management of campus departments, degree programs, and sections (CourseDepartment.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
System & Academic Settings | Document Management & Compliance Rules | Configure document categories, compliance checklists & submission rules (DocumentManagementSettings.tsx) | 🟣 Projected Plan | bar: OCTOBER 2026 W2 to OCTOBER 2026 W4
🟢 Complete (Actual) | bar: OCTOBER 2026 W3 to NOVEMBER 2026 W1
System & Academic Settings | Event Categories & Venues Management (CRUD) | Manage event categories, campus venues & capacity rules (EventConfiguration.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
System & Academic Settings | Attendance & QR Scanner Gate Rules | Configure QR scan windows, duplicate scan tolerance, lock policy (AttendanceQRSettings.tsx) | 🟣 Projected Plan | bar: OCTOBER 2026 W2 to OCTOBER 2026 W4
🟢 Complete (Actual) | bar: OCTOBER 2026 W3 to NOVEMBER 2026 W1
System & Academic Settings | Certificate Signatures & Resolution Settings | Set default SAO adviser signature, institution logo, export DPI resolution (CertificateSettings.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
System & Academic Settings | Liquidation Policy & Receipt Rules | Allowable expense categories, receipt upload policy, liquidation grace period (LiquidationSettings.tsx) | 🟣 Projected Plan | bar: OCTOBER 2026 W3 to NOVEMBER 2026 W1
🟢 Complete (Actual) | bar: OCTOBER 2026 W4 to NOVEMBER 2026 W2
System & Academic Settings | Event Absence & Late Fine Penalty Rules | Configure fine amounts per absence/late scan, automatic payable posting rules (FinePenaltyRules.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
System & Academic Settings | System Audit Logs Viewer | Hardcoded audit log table & static alert banner (AuditLogs.tsx) | 🟣 Projected Plan | bar: OCTOBER 2026 W3 to NOVEMBER 2026 W1
🟡 Incomplete (Actual) | bar: NOVEMBER 2026 W1 to NOVEMBER 2026 W3
System & Academic Settings | System General Settings & Preferences | 17 settings navigation menu UI without persistent Firestore write handlers (SystemSettings.tsx) | 🟣 Projected Plan
🟡 Incomplete (Actual)
Announcements | Global Announcement Feed & Stream | Live announcement stream feed (useAnnouncementStream), render priority badges (AnnouncementsDashboard.tsx) | 🟣 Projected Plan | bar: NOVEMBER 2026 W1 to NOVEMBER 2026 W3
🟢 Complete (Actual) | bar: NOVEMBER 2026 W2 to NOVEMBER 2026 W4
Announcements | Create & Post Announcement Modal | Compose announcement title, content, target audience, priority rating (CreateAnnouncementModal.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Announcements | Pin / Unpin Announcement Feature | Toggle announcement pinned status to feature on student dashboard feed (togglePin) | 🟣 Projected Plan | bar: NOVEMBER 2026 W1 to NOVEMBER 2026 W3
🟢 Complete (Actual) | bar: NOVEMBER 2026 W2 to NOVEMBER 2026 W4
Announcements | Target Audience & Priority Badges | Campus-wide, All Organizations, or Specific Organizations audience targeting & Urgent/Important badges | 🟣 Projected Plan
🟢 Complete (Actual)
2. OFFICER WEB APPLICATION
Officer Authentication | Organization Officer Login Gateway | Validate officer credentials, bind active org context (OfficerLogin.tsx) | 🟣 Projected Plan | bar: JUNE 2026 W2 to JUNE 2026 W3
🟢 Complete (Actual) | bar: JUNE 2026 W3 to JUNE 2026 W4
Officer Authentication | Active Org Context Binding & Route Guard | Switch active org context, verify officer permissions (useOfficerProfile) | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Dashboard | Good Day Welcome Banner & Org Context | Render officer welcome header, active org profile summary (OfficerDashboardPage.tsx) | 🟣 Projected Plan | bar: JUNE 2026 W3 to JUNE 2026 W4
🟢 Complete (Actual) | bar: JUNE 2026 W4 to JULY 2026 W1
Officer Dashboard | Overview Stat Metric Cards | Live streams for upcoming events, pending liquidations, total members, monthly events | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Dashboard | Upcoming Events Schedule Table & Status Badges | Display org scheduled events, dates, session times, proposal status pills | 🟣 Projected Plan | bar: JUNE 2026 W4 to JULY 2026 W2
🟢 Complete (Actual) | bar: JULY 2026 W1 to JULY 2026 W3
Officer Dashboard | Pending Action Items Tasks Queue | Real-time task list for returned liquidations, draft proposals, pending revisions with action links | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Dashboard | Real-Time Gate Attendance Stream Feed Table | Live stream of student check-in/check-out scans for org events | 🟣 Projected Plan | bar: JULY 2026 W1 to JULY 2026 W3
🟢 Complete (Actual) | bar: JULY 2026 W2 to JULY 2026 W4
Event Management | Org Proposal Listing & Status Tabs | Display org proposals with live status pills (Draft, Pending Review, Approved, Returned, Rejected) | 🟣 Projected Plan
🟢 Complete (Actual)
Event Management | Proposal Search & Category Filter Bar | Filter proposals by status tabs and search proposal title query | 🟣 Projected Plan | bar: JULY 2026 W1 to JULY 2026 W3
🟢 Complete (Actual) | bar: JULY 2026 W2 to JULY 2026 W4
Event Management | 7-Step Officer Event Proposal Wizard Modal | Details, Audience, Date/Venue, Program/Speakers, Budget Request, Docs, Submit (OfficerEventProposalModal.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Event Management | Draft Event Proposal Save & Resumption | Save proposal as draft, calculate completion step, resume draft in wizard | 🟣 Projected Plan | bar: JULY 2026 W3 to AUGUST 2026 W2
🟢 Complete (Actual) | bar: JULY 2026 W4 to AUGUST 2026 W3
Event Management | Edit & Resubmit Returned Proposal Modal | Modify draft/returned proposal, inspect SAO Adviser remarks, re-upload documents, resubmit | 🟣 Projected Plan
🟢 Complete (Actual)
Event Management | View Proposal Details & Status History Log | Detailed view of proposal info grid, budget breakdown, attached PDFs, status history timeline | 🟣 Projected Plan | bar: JULY 2026 W4 to AUGUST 2026 W2
🟢 Complete (Actual) | bar: AUGUST 2026 W1 to AUGUST 2026 W3
Attendance Logs | Org Event Live Attendance Stream Feed | Real-time scan monitoring for org events, entry timestamp log (AttendanceLogs.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Attendance Logs | Event & Session Window Filter Selector | Filter scan logs by org event & session window (Morning/Afternoon) | 🟣 Projected Plan | bar: AUGUST 2026 W2 to AUGUST 2026 W4
🟢 Complete (Actual) | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W1
Attendance Logs | Gate Attendance Scan Statistics Cards | Summary metrics for total checked in, on-time vs late, flagged scans | 🟣 Projected Plan
🟢 Complete (Actual)
Attendance Logs | Manual Attendance Override Entry Modal | Manually record student attendance for lost QR code or walk-in cases | 🟣 Projected Plan | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W2
🟢 Complete (Actual) | bar: AUGUST 2026 W4 to SEPTEMBER 2026 W3
Attendance Logs | Attendance Log Export to CSV | Export org event attendance list to CSV file (UI placeholder) | 🟣 Projected Plan
🟡 Incomplete (Actual)
Member Directory | Member Roster Table & Search by Name/ID | List org members, filter by course/year level, search student name (MemberDirectory.tsx) | 🟣 Projected Plan | bar: JULY 2026 W2 to JULY 2026 W4
🟢 Complete (Actual) | bar: JULY 2026 W3 to AUGUST 2026 W1
Member Directory | Course, Department & Role Filter Chips | Filter roster by department, course code, year level, and role (Member vs Officer) | 🟣 Projected Plan
🟢 Complete (Actual)
Member Directory | Member Overview Summary Cards | Metric cards for Total Members, Active Officers, Pending Applications | 🟣 Projected Plan | bar: JULY 2026 W2 to JULY 2026 W4
🟢 Complete (Actual) | bar: JULY 2026 W3 to AUGUST 2026 W1
Member Directory | Add New Member Modal (CRUD Create) | Search student database, add student to organization roster (AddMemberModal.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Member Directory | Appoint / Change Officer Role Modal | Assign officer positions: President, VP, Secretary, Treasurer, Auditor, PRO (AppointOfficerModal.tsx) | 🟣 Projected Plan | bar: JULY 2026 W3 to AUGUST 2026 W1
🟢 Complete (Actual) | bar: JULY 2026 W4 to AUGUST 2026 W2
Member Directory | Member Profile Details Slide-Over Inspector | Slide-over panel displaying student info, joined date, attendance record (MemberProfilePanel.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Member Directory | Deactivate / Remove Member Modal (CRUD) | Deactivate or remove student from org member roster (RemoveMemberModal.tsx) | 🟣 Projected Plan | bar: JULY 2026 W3 to AUGUST 2026 W1
🟢 Complete (Actual) | bar: JULY 2026 W4 to AUGUST 2026 W2
Member Directory | Member Attendance & Dues Compliance Ledger | Track individual member event attendance rate & dues payment status | 🟣 Projected Plan
🟢 Complete (Actual)
Finance Center | Financial Overview Summary Cards | Summary metrics for available org balance, total dues collected, pending liquidations, total expenses (FinanceCenter.tsx) | 🟣 Projected Plan | bar: AUGUST 2026 W2 to SEPTEMBER 2026 W1
🟢 Complete (Actual) | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W2
Finance Center | Org Dues & Student Payables Management Table | Track org membership dues & custom student payables ledger | 🟣 Projected Plan
🟢 Complete (Actual)
Finance Center | Generate Member Dues Modal (CRUD Create) | Set due amount, select target semester/batch, set due date, publish payable (GenerateDuesModal.tsx) | 🟣 Projected Plan | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W2
🟢 Complete (Actual) | bar: AUGUST 2026 W4 to SEPTEMBER 2026 W3
Finance Center | Custom Student Payable Modal | Assign specific fine or event registration fee to student (AddPayableModal.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Finance Center | Record Manual Cash Payment Modal | Mark student payable as Paid with Official Receipt # input (RecordPaymentModal.tsx) | 🟣 Projected Plan | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W2
🟢 Complete (Actual) | bar: AUGUST 2026 W4 to SEPTEMBER 2026 W3
Finance Center | Financial Liquidations Stream Table | Display submitted liquidations list, status badges, spending variance (FinancialLiquidation.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Finance Center | Submit Financial Liquidation Report Modal | Attach expense line items, upload scanned receipts, submit to SAO (OfficerLiquidationModal.tsx) | 🟣 Projected Plan | bar: AUGUST 2026 W4 to SEPTEMBER 2026 W4
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W1 to OCTOBER 2026 W1
Finance Center | Resubmit Returned Liquidation Report Modal | Resubmit liquidation report with updated expense items & SAO Adviser return notes | 🟣 Projected Plan
🟢 Complete (Actual)
Finance Center | Org Expense Ledger & Budget Balance Calculator | Real-time computation of org balance, spent funds, pending liquidations | 🟣 Projected Plan | bar: SEPTEMBER 2026 W1 to OCTOBER 2026 W1
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W2 to OCTOBER 2026 W2
Officer Document Center | Officer Document Center Dashboard & Metrics | Overview cards for total submitted, pending review, approved, unread inbox (OfficerDocuments.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Document Center | Submit Document to SAS Modal | Upload activity letters, waivers, accreditation papers to Cloudinary, submit to SAS (SubmitDocModal) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W2 to OCTOBER 2026 W1
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W2
Officer Document Center | Document Submissions Queue & Tracking Table | Live submissions stream (useOfficerSubmissions), search, reference number tracking | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Document Center | Resubmit Rejected Document Modal | Resubmit rejected document with corrected file upload & Adviser remarks inspector (ResubmitModal) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W1
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W2
Officer Document Center | Official SAS Memos & Broadcast Inbox | Live stream of received SAS memos/guidelines (useOfficerInbox), unread badge, mark read state | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Document Center | Full-Screen Document Preview Modal | High-fidelity PDF/image document viewer modal (DocumentPreviewModal) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W1
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W2
Officer Certificates | Org Certificate Templates Library Grid | Browse org certificate templates, filter by category (OfficerCertificates.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Certificates | Visual Drag-and-Drop Canvas Template Editor | Interactive canvas editor for org event certificates (TemplateEditor.tsx with org context) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W2
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W3
Officer Certificates | Batch Certificate Generator Engine | Batch generate certs for org event attendees (GenerateCertificates.tsx) | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Certificates | Full-Screen Preview & Export Modal | Full-screen cert preview, export to PNG/PDF/ZIP (ExportModal.tsx) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W2
🟢 Complete (Actual) | bar: OCTOBER 2026 W1 to OCTOBER 2026 W3
Officer Announcements | Post Organization Announcement Modal | Compose announcement title, content, priority rating, target audience (CreateModal) | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Announcements | Announcement Feed Stream for Org Members | Live stream feed of org announcements (useAnnouncementStream), tab filters (OfficerAnnouncements.tsx) | 🟣 Projected Plan | bar: NOVEMBER 2026 W1 to NOVEMBER 2026 W3
🟢 Complete (Actual) | bar: NOVEMBER 2026 W2 to NOVEMBER 2026 W4
Officer Announcements | Pin / Unpin Announcement to Top | Pin important announcement to top of member feed (togglePin) | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Announcements | Audience Filtering & Priority Badges | Target all members, by department, or by year level + Urgent/Important priority badges | 🟣 Projected Plan | bar: NOVEMBER 2026 W1 to NOVEMBER 2026 W3
🟢 Complete (Actual) | bar: NOVEMBER 2026 W2 to NOVEMBER 2026 W4
Officer Announcements | Link Announcement to Approved Org Event | Link announcement post directly to approved org event (selectedEventId dropdown) | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Settings | Account Profile Info & Contact Update | Update full name, contact number, email address (OfficerSettings.tsx) | 🟣 Projected Plan | bar: OCTOBER 2026 W1 to OCTOBER 2026 W3
🟢 Complete (Actual) | bar: OCTOBER 2026 W2 to OCTOBER 2026 W4
Officer Settings | Profile Photo Upload & Cloudinary | Upload officer profile photo to Cloudinary CDN, update student record | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Settings | Change Password & Strength Inspector | Update account password with strength meter & match validator | 🟣 Projected Plan | bar: OCTOBER 2026 W1 to OCTOBER 2026 W3
🟢 Complete (Actual) | bar: OCTOBER 2026 W2 to OCTOBER 2026 W4
Officer Settings | Active Sessions & Devices Manager | View active login sessions & devices, remote sign-out action | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Settings | Organization Identity Details Configurator | Update org name, acronym, type, department (OrganizationProfile.tsx) | 🟣 Projected Plan | bar: OCTOBER 2026 W1 to OCTOBER 2026 W3
🟢 Complete (Actual) | bar: OCTOBER 2026 W2 to OCTOBER 2026 W4
Officer Settings | Organization Logo Upload & Preview | Upload org logo image to Cloudinary, preview logo avatar | 🟣 Projected Plan
🟢 Complete (Actual)
Officer Settings | Mission & Vision Description Configurator | Update org mission/vision statements & general description | 🟣 Projected Plan | bar: OCTOBER 2026 W1 to OCTOBER 2026 W3
🟢 Complete (Actual) | bar: OCTOBER 2026 W2 to OCTOBER 2026 W4
Officer Settings | Active Officer Roles & Permissions Configurator | Configure granular permissions per officer role (UI placeholder) | 🟣 Projected Plan
🟡 Incomplete (Actual)
3. STUDENT MOBILE APPLICATION (FLUTTER)
Auth & Registration | Welcome & Splash Screens | App entry branding, auto login session check (splash_screen.dart, welcome_screen.dart) | 🟣 Projected Plan | bar: JUNE 2026 W1 to JUNE 2026 W2
🟢 Complete (Actual) | bar: JUNE 2026 W2 to JUNE 2026 W3
Auth & Registration | Student Login Screen | Firebase auth sign-in, password visibility toggle, error handling (login_screen.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Auth & Registration | Multi-Step Registration Flow Container | Step progress indicator, page controller navigation shell (registration_flow_screen.dart) | 🟣 Projected Plan | bar: JUNE 2026 W3 to JULY 2026 W2
🟢 Complete (Actual) | bar: JUNE 2026 W4 to JULY 2026 W3
Auth & Registration | Step 1: Personal Info Input | First Name, Last Name, Gender, Birthdate, Contact #, Address (personal_info_step.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Auth & Registration | Step 2: Academic Details Input | Student ID #, Department, Course, Year Level, Section (academic_details_step.dart) | 🟣 Projected Plan | bar: JUNE 2026 W3 to JUNE 2026 W4
🟢 Complete (Actual) | bar: JUNE 2026 W4 to JULY 2026 W1
Auth & Registration | Step 3: Account Credentials Input | STI Email, Password, Confirm Password with visibility toggles (credentials_step.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Auth & Registration | Step 4: School ID Upload & Gemini AI OCR | Camera capture ID card, Gemini AI text extraction & verification score check (school_id_step.dart) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W1 to SEPTEMBER 2026 W3
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W2 to SEPTEMBER 2026 W4
Auth & Registration | Step 5: Profile Photo Selfie & Cloudinary Upload | Capture selfie/photo, upload to Cloudinary CDN, save URL (profile_photo_step.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Auth & Registration | Step 6: Registration Review & Submit | Review full registration data, terms agreement checkbox, submit application (review_step.dart) | 🟣 Projected Plan | bar: JULY 2026 W1 to JULY 2026 W3
🟢 Complete (Actual) | bar: JULY 2026 W2 to JULY 2026 W4
Auth & Registration | Pending Account Verification Guard Screen | Display pending verification status notice, block unauthorized app access (pending_status_screen.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Dashboard & Digital ID | Dashboard Header Bar & Greetings | Render student avatar, greeting name, notifications trigger (dashboard_header.dart) | 🟣 Projected Plan | bar: JUNE 2026 W3 to JULY 2026 W1
🟢 Complete (Actual) | bar: JUNE 2026 W4 to JULY 2026 W2
Dashboard & Digital ID | Digital Student ID Card & Barcode Display | Render digital ID card, student photo, student number, barcode (digital_id_card.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Dashboard & Digital ID | Scanner Officer Assignment Launcher Banner | Auto-detect if student is assigned gate scanner, show scanner launcher button (scanner_assignment_banner.dart) | 🟣 Projected Plan | bar: AUGUST 2026 W1 to AUGUST 2026 W3
🟢 Complete (Actual) | bar: AUGUST 2026 W2 to AUGUST 2026 W4
Dashboard & Digital ID | Joined Organizations Banner | Horizontal scroll of student's joined orgs (my_organizations_section.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Dashboard & Digital ID | Campus Announcements Ticker Carousel | Broadcast announcements ticker carousel on dashboard (announcements_section.dart) | 🟣 Projected Plan | bar: JULY 2026 W2 to AUGUST 2026 W1
🟢 Complete (Actual) | bar: JULY 2026 W3 to AUGUST 2026 W2
Dashboard & Digital ID | Quick Actions Grid & Glass Navigation Shell | Glass bottom navbar, quick links to payables, events, QR ticket (quick_actions_grid.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Event Feed & Discovery | Featured Events Banner Carousel | Banner carousel of upcoming major campus events (featured_event_card.dart) | 🟣 Projected Plan | bar: JULY 2026 W1 to JULY 2026 W3
🟢 Complete (Actual) | bar: JULY 2026 W2 to JULY 2026 W4
Event Feed & Discovery | Event Search Query Bar | Search input bar to filter events by title or keywords (event_search_bar.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Event Feed & Discovery | Event Category Filter Chips | Filter events by category chips: Academic, Sports, Org, All (event_filter_chips.dart) | 🟣 Projected Plan | bar: JULY 2026 W2 to AUGUST 2026 W1
🟢 Complete (Actual) | bar: JULY 2026 W3 to AUGUST 2026 W2
Event Feed & Discovery | Upcoming Events Listing Cards | List view of upcoming events with date, venue, host badges (event_list_card.dart, upcoming_events_section.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Event Feed & Discovery | Event Details & Session Schedule Inspector Screen | Full event info, venue map, session schedule timeline, host details (event_detail_screen.dart) | 🟣 Projected Plan | bar: JULY 2026 W3 to AUGUST 2026 W2
🟢 Complete (Actual) | bar: JULY 2026 W4 to AUGUST 2026 W3
Event Feed & Discovery | Event Session Registration & Seat Confirmation | Register for event sessions, confirm attendance booking, update seat count | 🟣 Projected Plan
🟢 Complete (Actual)
QR Ticket Engine | Dynamic Encrypted QR Code Display Screen | Render secure encrypted QR code for event entry (qr_ticket_screen.dart, qr_code_display.dart) | 🟣 Projected Plan | bar: AUGUST 2026 W1 to AUGUST 2026 W3
🟢 Complete (Actual) | bar: AUGUST 2026 W2 to AUGUST 2026 W4
QR Ticket Engine | Session Selector Sheet for Event QR Ticket | Switch between morning/afternoon session QR tickets in bottom sheet | 🟣 Projected Plan
🟢 Complete (Actual)
QR Ticket Engine | Locked QR Gate Blocker Overlay | Red overlay when unpaid payable exists (locked_qr_card.dart: 'PAYMENT REQUIRED' hard stop) | 🟣 Projected Plan | bar: AUGUST 2026 W2 to AUGUST 2026 W4
🟢 Complete (Actual) | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W1
Student Payables & Dues | Total Balance Overview Card | Summary card of total unpaid balance, total paid, pending fees (payment_overview_card.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Student Payables & Dues | Financial Dues & Fines Category Tabs | Category tabs switcher for Dues, Fines, and Payment History (finance_tabs.dart, payables_screen.dart) | 🟣 Projected Plan | bar: AUGUST 2026 W2 to AUGUST 2026 W4
🟢 Complete (Actual) | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W1
Student Payables & Dues | Organizational Dues List View & Status Badges | Itemized breakdown of org membership dues & payment status (dues_list_view.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Student Payables & Dues | Event Registration Fees & Absence Fines List View | List event registration fees and absence fines with amount breakdown (fines_list_view.dart) | 🟣 Projected Plan | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W2
🟢 Complete (Actual) | bar: AUGUST 2026 W4 to SEPTEMBER 2026 W3
Student Payables & Dues | Transaction & Payment History Log | Historical log of paid items, dates, official receipt reference codes (history_list_view.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
In-App Mobile QR Scanner | Scanner Mode Launcher & Event Selector Screen | Select assigned event & gatekeeper mode (scanner_mode_screen.dart) | 🟣 Projected Plan | bar: AUGUST 2026 W2 to AUGUST 2026 W4
🟢 Complete (Actual) | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W1
In-App Mobile QR Scanner | Event Session Selector Bottom Sheet | Choose session window (Morning/Afternoon) for gatekeeping (session_selector_sheet.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
In-App Mobile QR Scanner | Live Camera QR Code Scanner Overlay | Fast QR camera scan, decode encrypted payload, instant haptic feedback (scanner_camera_screen.dart) | 🟣 Projected Plan | bar: AUGUST 2026 W3 to SEPTEMBER 2026 W1
🟢 Complete (Actual) | bar: AUGUST 2026 W4 to SEPTEMBER 2026 W2
In-App Mobile QR Scanner | Visual Verification Security Match Screen | Full-screen overlay showing scanned student photo, name, course, entry status (scan_result_overlay.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
In-App Mobile QR Scanner | Offline Event Roster Pre-Download Screen | Download event roster & student payable data to local SQLite DB prior to event (scanner_download_screen.dart) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W2
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W4 to OCTOBER 2026 W3
In-App Mobile QR Scanner | Manual Student Search Fallback | Search student by ID/Name when camera is unavailable or barcode unreadable (manual_attendance_screen.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
In-App Mobile QR Scanner | Gate Attendance Scan Logs & History Inspector | Inspect recorded scans, filter on-time vs late, view scan timestamp history (scanner_logs_screen.dart) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W1 to SEPTEMBER 2026 W3
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W2 to SEPTEMBER 2026 W4
In-App Mobile QR Scanner | Offline Sync Conflicts & Resolution Inspector | Display sync conflicts, manual resolution actions for duplicate offline scans (sync_conflicts_screen.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Offline Storage & Sync Engine | Offline Local SQLite Storage & Queue (Drift/Dao) | Store attendance scans locally when offline in SQLite queue (offline_attendance_table) | 🟣 Projected Plan | bar: SEPTEMBER 2026 W2 to OCTOBER 2026 W1
🟢 Complete (Actual) | bar: SEPTEMBER 2026 W3 to OCTOBER 2026 W2
Offline Storage & Sync Engine | Real-Time Connectivity Monitoring Daemon | Listen to internet connectivity changes, trigger background sync when back online (connectivity_service.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Offline Storage & Sync Engine | Background Attendance Auto-Sync Daemon | Background sync service with retry policy & conflict detection (sync_service.dart) | 🟣 Projected Plan | bar: OCTOBER 2026 W1 to OCTOBER 2026 W4
🟢 Complete (Actual) | bar: OCTOBER 2026 W2 to NOVEMBER 2026 W1
Offline Storage & Sync Engine | Offline Cache Cleanup & Expired Event Purge | Purge expired local event roster cache to free device storage (event_cleanup_service.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Profile & Settings | Student Profile Header & Identity Summary | Render student avatar, name, student ID, course & section (profile_header.dart, profile_screen.dart) | 🟣 Projected Plan | bar: JULY 2026 W1 to JULY 2026 W3
🟢 Complete (Actual) | bar: JULY 2026 W2 to JULY 2026 W4
Profile & Settings | Detailed Academic & Personal Information Card | Display academic details, email, contact #, department affiliation (profile_info_card.dart) | 🟣 Projected Plan
🟢 Complete (Actual)
Profile & Settings | Account Security & Password Update Card | Change password form, update security credentials, logout (profile_danger_card.dart) | 🟣 Projected Plan | bar: JULY 2026 W2 to JULY 2026 W4
🟢 Complete (Actual) | bar: JULY 2026 W3 to AUGUST 2026 W1
Organizations Portal | Accredited Organizations Directory List | Browse all accredited campus organizations with logos & acronyms | 🟣 Projected Plan
🟢 Complete (Actual)
Organizations Portal | Apply to Join Organization Bottom Sheet | Submit membership application & department details to org officers (join_organization_sheet.dart) | 🟣 Projected Plan | bar: JULY 2026 W3 to AUGUST 2026 W1
🟢 Complete (Actual) | bar: JULY 2026 W4 to AUGUST 2026 W2